BURTUCALA

90-Day Marketing Pivot

Red-Teamed & Optimized

March 25, 2026

Based on Burtucala Portal Meeting Analysis

Asaf Eyzenkot + Noam Perets

# Context

Meeting: Burtucala Portal Ongoing (March 25, 2026, 64 min)

Participants: Asaf Eyzenkot + Noam Perets

Core outcome: 3-month ultimatum (April-June). July 1st = go/no-go decision on Burtucala's future.

Both partners agree: the current content-heavy approach (8 articles/month, LinkedIn posts, Facebook group engagement) is structurally sound but emotionally flat.

Asaf's diagnosis: "It's mild, boring, lacking audacity. No pepper, no boldness. No conversion."

The strategy needs a Purple Cow transformation. Paulo agent is a separate workstream under RealizeOS, not part of this marketing plan.

# The Strategic Insight

What Burtucala IS doing: Publishing useful content that explains Portugal's business landscape to foreigners. Good SEO. Good structure. Professional voice.

What every other Portugal consultant is also doing: Exactly the same thing. Articles about AL licenses. Posts about golden visas. "Helpful tips for expats." The market is flooded with informational content.

What nobody is doing: Making people FEEL the problem. Hitting the emotional nerve. Being the one brand that says "I'll show you what a €200K mistake looks like" instead of "here are 5 tips for your renovation."

The Purple Cow formula: Take your biggest strength (brutal honesty + real operational experience) and AMPLIFY it to a level that makes competitors uncomfortable.

# Red Team Analysis

Each idea was stress-tested against: market resistance, people's feelings, cultural fit, realistic effort, and failure scenarios.

## IDEA #1: "The Anti-Pitch" (Contrarian LinkedIn Series)

Value-for-Effort: ★★★★★

Concept: Weekly LinkedIn posts where Asaf dismantles commonly repeated Portugal investment advice with data and experience. Provocative headlines, contrarian takes.

### Red Team Challenges

| Risk | Severity | Analysis & Fix |
| --- | --- | --- |
| Contrarian fatigue | Medium | If every post is "everyone is wrong," Asaf looks like a perpetual critic. Fix: Alternate 2 contrarian / 2 constructive posts per month. Contrarian hook draws attention; constructive follow-up builds trust. |
| Small community backlash | Med-High | Portugal's expat investment scene is tight. Calling out common advice indirectly calls out specific people. Fix: NEVER target people or companies. Target IDEAS and ASSUMPTIONS only. "This common assumption costs investors €40K" is bold. "Real estate agents mislead you" is hostile. |
| Algorithm shelf life | Low | LinkedIn posts disappear in 24-48h. Fix: Repurpose each Anti-Pitch as video clip, newsletter section, and blog reference. Create a flywheel. |
| Comment section control | Medium | Provocative posts attract angry comments. Fix: Asaf must engage 15 min/day on post days. Never defensive. Turn debate into proof of expertise. |

Verdict: PASSES with guardrails: alternate contrarian/constructive, target ideas not people, 15 min/day comment engagement, every post ends with value.

Monthly time cost: 3-4 hours (4 posts x 45 min + comment engagement)

Cost: Zero

## IDEA #2: "€200K Mistake" (Video Series)

Value-for-Effort: ★★★★

Concept: 3 short videos (3-5 min each) telling anonymized stories of Portugal ventures that went wrong. Specific numbers, real consequences.

### Red Team Challenges

| Risk | Severity | Analysis & Fix |
| --- | --- | --- |
| Fear-mongering perception | Med-High | Fear works ONLY when paired with a credible solution. The ICP (35-55, risk-averse) responds to "someone who understands my fear and shows me a way through." Fix: Structure every video as 40% fear / 60% solution. Always end with "here's what prevents this." |
| Authenticity doubts | Medium | Anonymized stories might seem fabricated. Fix: Use composite stories (blend multiple real situations). Add disclaimer: "Based on patterns from multiple projects." Asaf's calm delivery adds credibility. |
| Production quality | Medium | Too amateur undermines Burtucala's professional positioning. Fix: Phone camera is fine, but invest in a €30 lapel mic. Natural light. The bar is "would I share this on LinkedIn?" not Netflix. |
| Content exhaustion | Low | Fix: Cap at 3 videos not 5. Each covers a DIFFERENT mistake type: (1) licensing/legal, (2) financial/capex, (3) operational/design. Three is a series. Five is a rut. |
| Makes Portugal look bad? | Low | Message is "Portugal is great IF you do it right." It's pro-Portugal, anti-stupidity. The ICP is already worried about these risks. Acknowledging them builds trust. |

Verdict: PASSES refined to 3 videos (not 5), 40% fear / 60% solution structure, lapel mic required, composite stories with disclaimer.

Total time cost: 5-6 hours for all 3 videos (then done, evergreen content)

Cost: €30 one-time (lapel mic)

## IDEA #3: "Live Deal Review" (formerly "Hot Seat")

Value-for-Effort: ★★★★

Concept: Monthly live session where 2-3 entrepreneurs present their Portugal venture concept. Asaf gives real-time, honest, numbers-based feedback on camera.

### Critical Rebranding Note

Renamed from "The Hot Seat" to "Burtucala Live Deal Review" or "Open Office Hours." The framing is "free expert analysis" not "public roasting." This is critical for getting applicants.

### Red Team Challenges

| Risk | Severity | Analysis & Fix |
| --- | --- | --- |
| Nobody applies | HIGH | The ICP (35-55, risk-averse) won't seek public vulnerability. "Hot Seat" is intimidating. Fix: Rebrand to "Live Deal Review." Value prop = FREE EXPERT ANALYSIS, not scrutiny. Pre-screen via form. 5-min pre-call with each participant to build comfort. |
| Low attendance | HIGH | Niche audience, no webinar track record. Getting 15+ is ambitious. Fix: Set real target at 8-12 for session #1. Position as "intimate session, limited seats." Personal invitations from LinkedIn/email. 8 engaged > 30 passive. |
| Cultural sensitivity | Medium | Israelis handle directness; Brits/Dutch/Germans may not. Fix: Pre-call sets expectations. Asaf's natural style is respectful: he quantifies, doesn't mock. |
| Effort underestimated | Medium | It's NOT "just show up." Need: application form, screening, prep, hosting, follow-up, clip editing. Reality: 4-5 hours per session. Half-day per month. Still worth it for qualified leads. |
| No follow-up path | Medium | Fix: Every reviewed participant gets personal follow-up within 24h. Non-selected applicants get Fit Call invitation. Both groups convert. |

Verdict: PASSES with significant reframing: rename to "Live Deal Review," pre-call with presenters, target 8-12 for session #1, structured follow-up for ALL applicants, EN first (HE only if EN works).

Monthly time cost: 5 hours per session (screening, prep, live, follow-up)

Cost: Zero (Zoom/Meet)

## ELIMINATED: "Walk & Talk" (Physical Pop-Ups)

Value-for-Effort: ★★★ (eliminated)

| Risk | Severity | Why It Fails |
| --- | --- | --- |
| Wrong audience | HIGH | Coworking spaces are full of digital nomads, not investors with €150K-2M. The ICP isn't at NomadX. They're in their apartments doing research or not in Portugal yet. |
| Uncontrollable variables | HIGH | Filming permissions, ambient noise, people who don't approach, conversations that go nowhere. Ratio of usable content to wasted time could be terrible. |
| Brand positioning risk | Medium | "Guy with a sign at a cafe" could read as desperate rather than audacious. The line between bold and weird is thin. |

Alternative if you still want physical presence: Pre-announced "Burtucala Office Hours" at a fixed location, with a booking link. People sign up for 15-min slots. Only happens if enough sign up. Consider as Month 3 experiment ONLY if the other 3 ideas are generating traction.

# Final 3 Campaigns, Ranked

Ranked by value-for-effort. Together they form a natural funnel.

| # | Campaign | Value/Effort | Role in Funnel | Monthly Cost |
| --- | --- | --- | --- | --- |
| 1 | The Anti-Pitch (LinkedIn) | ★★★★★ | THE MAGNET: draws attention, builds audience | 3-4 hrs/month, €0 |
| 2 | €200K Mistake Videos | ★★★★ | THE TRIGGER: creates emotional urgency | 5-6 hrs TOTAL (then done), €30 |
| 3 | Live Deal Review | ★★★★ | THE CONVERTER: generates qualified leads | 5 hrs/session, €0 |

How they work together: Anti-Pitch builds awareness on LinkedIn → €200K videos create emotional urgency → Live Deal Review captures qualified leads. It's a funnel, not isolated campaigns.

# The 90-Day Battle Plan

## Month 1: April — "Light the Match"

| Week | Action | Owner | Output |
| --- | --- | --- | --- |
| 1 | Anti-Pitch post #1: "Stop saying Portugal is cheap. Here's what things actually cost." | Asaf | LinkedIn post + engagement |
| 1 | Design Live Deal Review: format, application form, landing page | Noam + Sofia | Application form live |
| 2 | Anti-Pitch post #2: "I told 3 investors NOT to invest. Here's why." | Asaf | LinkedIn post |
| 2 | Record €200K Mistake video #1 (licensing mistake) | Asaf | Posted on LinkedIn + YouTube |
| 3 | Anti-Pitch post #3 (constructive): "The 3 checks I run before any deal." | Asaf | LinkedIn post |
| 3 | Record €200K Mistake video #2 (financial/capex mistake) | Asaf | Posted |
| 3 | Promote Live Deal Review #1: LinkedIn, email list, personal DMs | Noam | 8+ applications |
| 4 | Live Deal Review #1 (EN) — review 2-3 concepts live | Asaf | 8-12 attendees |
| 4 | Anti-Pitch post #4 (constructive): "What a €2,800 diagnostic actually produces." | Asaf | LinkedIn post |
| 4 | Follow-up all applicants (selected + non-selected) | Noam | Fit Call invitations sent |
| 4 | Publish 2 support articles (Boutique Hotel Numbers + Emails to Bureaucrats) | Sofia | Published on blog |

April targets: 4 Fit Calls booked, 1 Blueprint request, 10+ Live Deal Review applications, 3%+ LinkedIn engagement rate, 500+ combined video views

## Month 2: May — "Build the Fire"

| Week | Action | Owner | Output |
| --- | --- | --- | --- |
| 1-2 | Anti-Pitch posts #5-#6 (1 contrarian + 1 constructive) | Asaf | LinkedIn posts |
| 1 | Record €200K Mistake video #3 (operational/design) — final video | Asaf | Posted, series complete |
| 2 | Promote Live Deal Review #2 | Noam | 12+ applications |
| 2-3 | Anti-Pitch posts #7-#8 | Asaf | LinkedIn posts |
| 3 | Live Deal Review #2 (EN) | Asaf | 12-18 attendees |
| 4 | Direct LinkedIn outreach: 30+ personal DMs to ICP contacts | Noam | 5+ responses, 3+ Fit Calls |
| 4 | Mid-sprint check: Are Fit Calls converting? What's working? Adjust. | Both | Decision on June approach |

May targets: 6 Fit Calls booked (cumulative: 10), 2 Blueprint requests (cumulative: 3), 25+ Live Deal Review applications total, 1+ paid engagement started

## Month 3: June — "Prove It"

| Week | Action | Owner | Output |
| --- | --- | --- | --- |
| 1-2 | Anti-Pitch posts #9-#12 | Asaf | LinkedIn posts |
| 2 | Live Deal Review #3 (EN) — with a guest co-host for amplification | Asaf | 20+ attendees |
| 3 | Optional: Live Deal Review (HE) — only if EN proved the model | Asaf | Bonus |
| 3-4 | Full metrics review. Prepare July 1st decision. | Both | Go/no-go brief |

June targets: 8 Fit Calls booked (cumulative: 18), 3 Blueprint requests (cumulative: 6), 40+ applications total, 1+ Sprint 0 started, €5,000+ revenue

# July 1st Decision Framework

The bar for Burtucala to continue:

| Signal | Minimum to Continue | Stretch (Strong) |
| --- | --- | --- |
| Fit Calls booked (total) | 12+ | 20+ |
| Blueprint / Strategy revenue | €2,500+ | €5,000+ |
| Sprint 0 engagements | 1 started | 2+ started |
| Total service revenue | €5,000+ | €15,000+ |
| Live Deal Review demand | 30+ applications | 50+ applications |
| Qualitative signal | "People recognize Burtucala" | "People refer others to us" |

- Minimum NOT met: Close Burtucala as discussed. Market isn't responding.

- Minimum met, stretch not: Continue with adjustments. Model works but needs optimization.

- Stretch met: Double down. Add Hebrew track, Operators Room, physical Office Hours.

# Anti-Pitch Topic Bank (12 Posts)

Each post follows: Contrarian hook → Data/experience → What to do instead → Soft CTA

C = Contrarian, V = Value/Constructive. Alternating pattern.

| # | Month | Type | Headline | Pillar |
| --- | --- | --- | --- | --- |
| 1 | Apr | C | "Stop saying Portugal is cheap. Here's what things actually cost in 2026." | P2: Investment |
| 2 | Apr | C | "I told 3 investors this month NOT to invest. Here's why." | P2: Investment |
| 3 | Apr | V | "The 3 checks I run before looking at any Portugal deal. Takes 20 minutes." | P2: Investment |
| 4 | Apr | V | "What a €2,800 diagnostic actually produces. Full output. No secrets." | P1: Energy |
| 5 | May | C | "The AL license gold rush is over. Here's what's actually working now." | P4: Biz OS |
| 6 | May | V | "One renovation decision saved a client €35K. It took 10 minutes." | P3: Design |
| 7 | May | C | "Your architect designs beautiful spaces that lose money. Here's the math." | P3: Design |
| 8 | May | V | "The 4 numbers that tell you if a boutique hotel deal works." | P2: Investment |
| 9 | Jun | C | "Everyone is excited about the Algarve. The smart operators are looking elsewhere." | P2: Investment |
| 10 | Jun | V | "How we turned a bad deal into a viable one by changing one variable." | P3: Design |
| 11 | Jun | C | "The most expensive words in Portugal RE: 'My agent said it would be fine.'" | P1: Energy |
| 12 | Jun | V | "3 years of Portugal ventures. The 5 patterns that predict success." | P1: Energy |

### Guardrails for Every Post

- Target IDEAS and ASSUMPTIONS, never specific people or companies

- End with value: "here's what to do instead" or "here's what works"

- Asaf engages with comments for 15 min on posting day

- No hashtag spam (3 max, per brand voice guide)

# €200K Mistake Video Specs

3 videos. One per mistake category. Each follows this structure:

| # | Working Title | Key Message |
| --- | --- | --- |
| 1: Licensing | "He bought the building before checking the license." | Municipal zoning + AL saturation = €200K trapped in an unlicensable property |
| 2: Financial | "The renovation budget was €150K. The final bill was €280K." | Capex underestimation without Fiscalização + contractor misalignment |
| 3: Operational | "Beautiful space. Losing €2,400/month." | Architect optimized for aesthetics, not revenue per sqm. No space program. |

### Video Structure (3-5 min each)

- Hook (15 sec): "This investor lost €200K because of one check he skipped."

- The Story (90 sec): What happened. Specific but anonymized. Numbers. Timeline.

- Root Cause (60 sec): Why it went wrong. The assumption that killed it.

- Prevention (60 sec): "Here's the check that would have caught this in 30 minutes."

- Bridge (15 sec): "This is exactly what Sprint 0 diagnoses before you commit capital."

### Production Requirements

- Phone camera (iPhone quality is fine)

- Lapel mic (€30, essential for audio)

- Natural light, quiet environment (cafe, office, or construction site)

- Text overlay with headline + key numbers (Sofia in CapCut or similar)

- End card: "Don't make these mistakes. Book a Fit Call at burtucala.com"

- Distribution: LinkedIn native video, YouTube, Instagram Reels

# Live Deal Review — Operational Playbook

### Session Format

- Duration: 75 min

- Participants: 2-3 presenters (pre-screened via application)

- Audience: 8-20 viewers (growing over time)

- Platform: Zoom (allows recording + breakout rooms)

### Session Flow

- Pre-session (1 week before): Noam screens applications, selects 2-3, does 5-min pre-call with each to set expectations

- Live (75 min): 5 min intro + ground rules → 15 min per concept (5 min pitch, 10 min review) → 10 min open Q&A → 5 min wrap + announce next session

- Post-session (within 24h): Personal follow-up to presenters with recommended next step. Non-selected applicants get Fit Call invitation. 2-3 highlight clips extracted for LinkedIn.

### Application Form Fields

- Name, email, phone

- Venture type (dropdown: hotel, guesthouse, cafe/restaurant, cowork, wellness, other)

- Location (city/region in Portugal)

- Budget range (dropdown)

- Timeline (when do you want to launch?)

- Brief description (2-3 sentences)

- "Are you comfortable with your concept being discussed in a live format?" (consent)

April 1 → July 1

90 days. 3 campaigns. Full power. No more hiding behind the keyboard.